## Slide 1
Medumba.ai
Implementation Roadmap
Now → NKONI Festival, Bronx NY
July 25–26, 2026
March
(Week 2–5)
April
(Mo. 2)
May
(Mo. 3)
June
(Mo. 4)
July
NKONI
SCOPE
7 Products · Homepage · Living Dictionary
BUILDER
Félix II Njandja Noumi
TECH LEAD
Tangyie Shulem Yaweni
CONTENT
Franklin Metchezin (Zenu) — NCOBNKUN
METHOD
Claude First — every task starts with Claude Code
NKONI
July 25–26, 2026 — Bronx, New York

## Slide 2
OVERVIEW
Master Timeline — March → June 30, 2026
MARCH
Weeks 2–5
APRIL
Month 2
MAY
Month 3
JUNE
Month 4
🌐 Homepage + Website
Homepage v1 deploy · Community links · eMuseum preview · Book section · Registration
App download section · Bundle activation · NKONI countdown · Word of Day widget
Medumba translation (Franklin) · QA · Amira Test · Cloudflare performance
Pre-NKONI final QA · UAT with Toundzi family · All sections verified
📖 Living Dictionary
Trilingual search live · Tonal audio · STEM domain · Category filters · word_suggestions table
New word pipeline: AI intake agent · NCOBNKUN dashboard (Franklin) · Gamification credits
STEM vocabulary seeded (50+ words) · User notification pipeline · Contributor leaderboard
Flutter dictionary module · Modern life domain (50+ words) · THEO integration verified
📱 App (Web + Mobile)
AI Translator live · THEO API auth + emitTheo()
Learning modules (5 types) · XP + streaks · Pronunciation AI · Flutter Android scaffold
iOS TestFlight · Android APK · Offline sync (TheoEventService + SyncService) · QR CEPOM
Voice query live · Full offline mode · UAT Donovan/Sara/Amira · Demo rehearsal
🎓 Live Classes Marketplace
DB schema: tutors, class_bookings, assessments, payouts, escalation_queue · Tutor portal
Assessment flow · TutorMatchingService · Daily.co integration · Stripe split + Wise
Post-class AI pipeline (Claude transcript → summary + THEO) · AI customer service chatbot
NKONI MVP: 3+ validated tutors · Booking flow live · Demo class confirmed · Donovan books
🏛️ eMuseum + AI Chatbot
Sanity CMS + 14-dim schema · eMuseum React frontend · Homepage preview
QR scan-to-draft pipeline · 50+ artifacts live · Chatbot RAG pipeline + ASR endpoint
FESTAC ingestion workflow · Chatbot voice query end-to-end · F1 baseline eval
All 50+ artifacts verified · Voice query demo-ready · THEO events flowing
★ NKONI FESTIVAL — BRONX, NEW YORK — JULY 25–26, 2026 — ALL PRODUCTS LIVE

## Slide 3
MONTH 1 — NOW
March 2026 (Weeks 2–5) — Build the Foundation
P0
THEO API: Supabase JWT auth + emitTheo() shared function
Everything else depends on this. Build first. No product ships until emitTheo() exists.
Felix + Aymar
P0
Supabase schema: ALL tables for all 7 products + word_suggestions
CREATE TABLE + RLS policies in one migration batch. Use Claude Code to generate full schema.
Felix
P0
Homepage v1: hero + 3-component cards + registration + community links
Deploy to medumba.ai via Vercel. Zenu YouTube embed. CEPOM + NCOBNKUN links. FR/EN.
Felix (Kaaynos pro bono)
P0
Dictionary v2: trilingual search + tonal audio + STEM domain + category filters
Extends MVP. Claude Code generates v1. Franklin seeds STEM vocabulary (Mathematics + CS priority).
Felix + Franklin
P0
New word pipeline: POST /words/suggest + AI intake agent (agentic Claude)
FAISS duplicate check · Claude drafts trilingual entry · routes to NCOBNKUN queue. Franklin gets dashboard.
Felix + Claude API
P1
eMuseum: Sanity CMS 14-dim schema + React frontend (/museum route)
Homepage preview gallery (5 artifacts). Cloudflare CDN configured. Franklin starts curating artifacts.
Felix + Franklin
P1
AI Translator v2: FR→Medumba live on medumba.ai (extends MVP)
Modal.com LLM endpoint. User feedback loop → LLM training signal. Rate limiting.
Felix + Tangyie
P1
Tutor onboarding portal: application form + Franklin validation queue
Stripe Connect onboarding. Availability calendar. Franklin reviews first 3 tutor applications.
Felix
March Milestone: theo_events flowing · Homepage live · Dictionary v2 · New word pipeline · eMuseum preview · Tutor portal

## Slide 4
MONTH 2
April 2026 — Build the Products
P0
Flutter scaffold: Android primary + iOS secondary
All screens by Claude Code. Riverpod + sqflite + GoRouter + Supabase Auth. NOT Firebase Auth.
Felix
P0
Learning modules: 5 lesson types + XP + streaks + progress_logs + THEO
SRS algorithm. Diaspora vs community tracks. emitTheo(lesson_completed) in every route.
Felix
P0
Pronunciation AI: FastAPI + librosa + Modal.com + Chart.js pitch contour
POST /assess-pronunciation. Score 0-100. tone_errors[]. teacher_override route. THEO event emitted.
Felix + Tangyie/GWU
P0
Tutoring: Assessment flow + TutorMatchingService + Stripe + Daily.co
AI scheduling → free 15-min Daily.co call → AI scoring → top 3 tutor cards → Stripe PaymentIntent.
Felix
P0
Post-class pipeline: Daily.co transcript → Claude → summary + THEO event
class_completed = richest THEO signal. 30–45 min real Medumba. Session summary email via SendGrid.
Felix + Claude API
P1
STEM vocabulary: 50+ words seeded by Franklin (Maths + CS priority)
Franklin creates words using NCOBNKUN dashboard. Each enters via word_approved_and_added THEO event.
Franklin
P1
eMuseum: QR scan-to-draft + 50+ artifacts live
Agentic Claude batch-generates descriptions. Franklin approves. Cloudflare CDN verified <2s Cameroon.
Felix + Franklin
P1
AI Chatbot: RAG pipeline (FAISS + OWL) + ASR voice endpoint
Flag Yaweni before running GPU fine-tuning job. FAISS wired to Medumba corpus + Jena Fuseki OWL filter.
Felix + Tangyie
April Milestone: Flutter apps running · Lessons + Pronunciation live · Tutoring booking flow · 50+ artifacts · STEM vocabulary · RAG chatbot

## Slide 5
MONTH 3
May 2026 — Polish + AI Operations
P0
iOS TestFlight build + Android APK sideloadable
Fastlane build config. TestFlight binary. Play Store metadata. APK for Toundzi UAT (Donovan, Sara, Amira).
Felix
P0
Offline-first Flutter: TheoEventService + SyncService + sync_queue
App offline → SQLite cache · lessons + dict · events queued → batch push on reconnect. Amira Test.
Felix
P0
Parent dashboard + family_links + goal_weights_set → PPO wiring
Parent goal sliders (academic / cultural / community). goal_weights_set event fires PPO update immediately.
Felix + Aristide
P0
AI customer service chatbot for Live Classes (95%+ queries)
Claude API + knowledge base (all booking/payment/class policies). Escalates at confidence < 0.85 to escalation_queue.
Felix + Claude API
P0
Voice query end-to-end: ASR → LLM → RAG → response · F1 baseline
Full agentic flow. ClickHouse logs F1. Dataset packaged for Aristide/GWU. Demo rehearsal.
Felix + Tangyie
P1
Gamification: credits leaderboard + contributor badges + dictionary attribution
Public leaderboard. Badge icons. 'Suggested by [username]' on every approved dictionary entry.
Felix
P1
Modern life vocabulary: 50+ diaspora daily words (Franklin + Toundzi input)
subway · semester · mortgage · graduation · social media · video call. Franklin + diaspora community input.
Franklin + Aristide
P1
FESTAC recurring pipeline + eMuseum QR codes for Chiefdom Palace install
Festival → eMuseum ingestion. Print-ready QR labels. Physical install at Bangangté Chiefdom Palace.
Felix + Franklin
May Milestone: Flutter TestFlight · Offline sync · Parent dashboard · AI chatbot · Voice query + F1 · Leaderboard · Modern vocab · Tutoring AI ops

## Slide 6
MONTH 4
June 2026 — Integration, UAT & NKONI Rehearsal
P0
NKONI demo rehearsal: all 7 products live end-to-end
Agentic Claude health check across all products. Claude Code patches any failing endpoints. 99% uptime verified.
Felix + Tangyie
P0
UAT Phase 1–6: Donovan (15) leads. Sara Marie (11). Amira (6) observed.
6-phase UAT: Dictionary → Lessons → Pronunciation → Media → Flutter offline → Full 30-min loop.
Toundzi family + Felix
P0
Amira Test audit: every PR that touches mobile UI must pass before merge
Every element: icon+text · one-tap audio · lesson steps ≤90s · animated celebration · 30-day session.
Felix
P0
New word pipeline: 1 full cycle completed (end-to-end demo ready)
Suggestion → AI draft → Franklin NCOBNKUN review → CEPOM approval → user notified + credited. Demo-ready.
Felix + Franklin
P0
Live Classes: 3+ Franklin-validated tutors confirmed · Booking flow live
Franklin completes linguistic validation of 3+ tutors. Assessment scheduling tested. Stripe live in test mode.
Felix + Franklin
P0
THEO API: 99% uptime · OpenAPI spec published · all products verified
All 7 products + homepage emit to theo_events. Twin initialization confirmed for Donovan, Sara Marie, Amira.
Felix + Tangyie
P1
medumba.ai Medumba-language homepage: Franklin validates all Medumba copy
Trilingual toggle FR/EN/Medumba. Franklin reviews and approves Medumba text. Milestone: homepage in Medumba.
Felix + Franklin
P1
Books: /books page live · Amazon affiliate links · bundle activation tested
Franklin provides book ASINs + Amazon affiliate tag. Bundle activation endpoint tested with real purchase.
Felix + Franklin
June 30 Milestone: All 7 products demo-ready · UAT complete · 3+ tutors validated · New word cycle proven · 99% API uptime · NKONI rehearsed

## Slide 7
DEFINITION OF DONE
NKONI Festival — July 25–26, 2026 — Done When
🌐 Homepage
✓ medumba.ai live, all sections, trilingual
✓ Zenu YouTube embedded (@zenumen7363)
✓ CEPOM + NCOBNKUN links active
✓ Book section + Amazon links
📖 Dictionary
✓ Trilingual search live (FR/Medumba/EN)
✓ Tonal audio one-tap for all entries
✓ STEM domain: 50+ validated words
✓ 1 full new word pipeline cycle demonstrated
📱 The App
✓ Web: Dictionary + Translator + Lessons + Pronunciation + Voice Query
✓ iOS: TestFlight on Donovan, Sara, Amira
✓ Android: APK sideloadable at NKONI
✓ Offline mode verified (airplane mode test)
🎓 Live Classes
✓ Booking flow live (Stripe in test/live mode)
✓ 3+ Franklin-validated tutors
✓ 1 demo class on stage — Donovan books live
✓ AI post-class summary demonstrated
🏛️ eMuseum + Chatbot
✓ 50+ artifacts live on eMuseum
✓ Voice query in Medumba demonstrated
✓ F1 baseline logged + dataset packaged
✓ FESTAC pipeline ready for future events
⚙️ THEO + Data
✓ All 7 products writing to theo_events
✓ THEO twin active for Donovan + Sara + Amira
✓ CEPOM pipeline: ≥3 records/week
✓ OpenAPI spec published
★ NKONI FESTIVAL · BRONX, NEW YORK · JULY 25–26, 2026 ★

## Slide 8
NKONI
July 25–26, 2026
Bronx, New York
★ All 7 products + homepage live at medumba.ai
★ Voice query in Medumba demonstrated on stage
★ Donovan books the first live class — on stage
★ Amira explores the dictionary — on stage
★ 50+ eMuseum artifacts · CEPOM pipeline running
★ New word pipeline cycle completed + demoed
★ THEO twins active for NKONI attendees
Builder
Félix II Njandja Noumi
Tech Lead
Tangyie Shulem Yaweni
Language/Culture
Franklin Metchezin (Zenu)
Platform + Strategy
Aristide Toundzi
Youth Ambassadors + UAT
Donovan · Sara Marie · Amira
medumba.ai · kaaynos.com